ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Albania

## Contracting authority

The contracting authority for this external expertise is Ministry of Agriculture and Rural Development (MARD), as Lead Partner (LP) of the thematic project ‘’Sustainable and innovative Agro food and fisheries value chain for MSME’s cross border market”, Food4Health No. 357 Reference, financed under Interreg Programme Italy-Albania – Montenegro.

## Country background

Albania is positioned in South-East Europe, in the western part of the Balkan Peninsula. Albania has a total area of 28,748 square kilometers. The total length of the border line is 1,094 km, of which 657 km are land border, 316 km of seaport, 48 km of river border and 73 km of lake border. In the northern part, Albania borders with Montenegro, in the north-east it borders on Kosovo, east bounded by North Macedonia, while in the south borders with Greece. In the western part, Albania has natural borders on the Adriatic and Ionian seas.The population of Albania on January 1, 2021 is 2,829,741 inhabitants, experiencing a decrease of 0.6%, compared to January 1, 2020

In Albania, agriculture is the most important contributor to the economy with almost 18.9% of the total of gross domestic product (GDP). Services, dominated by wholesale and retail trade, real estate, transport, and storage services, account for 48.6% (GDP) and 43.4% of employment (INSTAT, 2021; World Bank, 2021). Industry, including construction, contributes 20.2% to GDP, with the highest contribution coming from the construction sector (10.8% of GDP) (INSTAT, 2021). Meanwhile, the manufacturing sector is very small, contributing just 6.3% to Albania’s GDP.

Despite a decline over the past decade, agriculture, forestry and fishing remains a very important sector in Albania, accounting for 18.9% of GDP, 36.5% of formal employment and a significant share of informal employment.

Albania has transitioned from a centrally planned economy to a democracy with a market-based economy as a potential candidate country for EU membership, Albania has opportunities for greatly improved economic performance.

There exist approximately 350,000 agricultural businesses, the majority of which are subsistence farmers. The farm structures are small and complex with an average farm size of 1.2 ha and fragmented into 3-5 plots of different size and land quality.

Agricultural development is a very important contributor to wider rural development – but it is not the only contributor. To be sustainable, rural populations and communities require a balance of economic and social resources, services, activities and infrastructures. These include good access to quality health, education and transport services, jobs and other income generating activities, vocational and other skills training, good quality infrastructure including roads, electricity, water, waste management and phone and internet, all contributing to rural areas as desirable places to live in healthy and sustainable environments. Development should also prioritise climate change mitigation and adaptation actions.

## Current situation in the sector

The Albanian agricultural sector is of crucial importance with regard to the socio-economic development of the country. It contributes around 18.9% to the country’s GDP and accounts for 36.5% of the overall employment (Instat, 2021a). Nearly 50% of the population is rural. The sector is characterised by a majority of small family farms with a low degree of commercialisation. However, the production of selected fruits and vegetables increased substantially during recent years.

In agri-food sector this includes significantly increased exports and import substitution through improved quality and product added value. From 1995 productivity doubled and is now around 3.500 USD per worker in the sector (source, World Bank). Although a positive trend, agriculture productivity is still 5 times less than in Greece, and 15 times less than in Austria – two countries that still have a number of smaller farmers and share of extensive agriculture. This clearly shows development potential of the agriculture sector. There are also significant challenges withstanding competitive pressures as EU integration advances. Aspects requiring considerable investment and development include: food standards, traceability and safety systems and compliance (including veterinary and phytosanitary controls); environmentally sustainable agriculture, preserving biodiversity, soil and water quality and restoring fragile ecosystems; mitigating and adapting to the effects of climate change. Adoption of the body of laws and regulations (including EU Acquis Communitaire) and enforcement all the way through the value chain by relevant institutions is needed in moving towards integration with the EU’s Common Agricultural Policy (CAP). All these aspects require greatly enhanced levels of innovation and major improvements in efficiency and waste reduction along with access to new knowledge and types of technology.

The new strategy is in line with the strategic objectives of NSDI II, the vision, objectives and priorities of the Government of Albania, in accordance with NPEI 2021-2023 (in relation to chapters 11, 12 & 13). The SARDF considers the strategic framework and methodology of Common Agricultural Policy (CAP); the objectives of the Common Fisheries Policy (CFP) and integrates the measures set out in Pillar V of the Western Balkans Green Agenda, agrobiodiversity strategy, etc.

The SARDF contains four general objectives:

- Promoting the production and quality of sustainable food through the development of a competitive and innovative agri-food sector;

- Strengthening the sustainable management of natural resources and climate action;

- Strengthening the socio-economic structure of rural areas;

- Fostering sustainable maritime and inland water development;

And two crosscutting objectives:

- Strengthening institutional and administrative capacities towards EU acquis alignment

- Transfer of knowledge and innovation

Although the challenges ahead there is good potential for expansion in the agri-food sector. There exist good agro-climatic conditions, there are great opportunities for increasing food exports and for import substitution as integration with the EU single market proceeds and initiatives in the country.

## Related programmes and other donor activities

German Government Funds: Project - Sustainable Development of Rural Areas in Albania (SDRA)

Objective, project purpose and components of the project:

The objective of this Project is to improve the preconditions for sustainable income opportunities in rural areas. Economic diversification in rural areas and increased competitiveness of the agricultural sector will contribute to a creation of more income of the rural population.

The project is developed on four areas of intervention which include:

- Policy & Strategy Advice for Rural Development: support to need-based strategies and policies for an agricultural and rural development aligned to EU requirements and absorption of IPARD funds;

- Promotion of selected Value Chains in Agriculture & Rural Tourism: selection of value chains to be supported through the project (marked-oriented agricultural value chains and traditional products; rural tourism products);

- Improvement of Education & Training in Agriculture & Rural Tourism: based on existing training providers’ improvement of needs-based trainings in agriculture and rural tourism;

- Strengthening Knowledge on Agriculture & Rural Development: support to advisory services; NGOs, and other relevant actors to strengthen transfer of knowledge and innovation in agriculture and rural development.

- Supporting businesses to cushion the economic effects of the Covid-19 Pandemic: with an advisory facility named “CoSolve-19” MSMEs in agriculture, tourism and other sectors are supported with a combination of advisory services and coaching on company level and grants. CoSolve-19 is jointly implemented with the BMZ funded project ProSEED. Grants will be managed by SRD while most experts´ contracts for the advisory services are managed by ProSEED. A joint steering structure with partner ministries of both projects will ensure sound implementation of CoSolve-19.

IPA 2016 “Support to food safety, veterinary and phytosanitary standards”

Objective, project purpose and components of the project:

This project aims to contribute to an increased protection of human, animal and plant health at every stage of the food production process, through the establishment of institutional and administrative capacities in line with the overall public administration reform agenda.

The project is developed under 3 specific objectives which are focused on:

(1)To assist the restructuring of the relevant administrative structures and ensure the building of appropriate capacities to implement policy measures and achieve strategic objectives in line with general public administration reform efforts and EU membership requirements’;(2) To raise public awareness ensuring that consumers are adequately informed about their choices, roles, responsibilities, and increasingly demand safe and high-quality food products’; (3) To help develop the necessary legal and institutional framework and design and implement the required policy measures to ensure progress towards strategic objectives in the field of food safety, veterinary and phytosanitary standards’.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

To enhance the competitiveness of MSMEs and favour the access to market in the cross-border area through the improvement of production techniques, the transfer, sharing and adoption of European quality standards and the enhancement of typical and traditional products of the agri-food sector and fisheries. The main results expected from the project are:

a) Enhanced MSME’s cooperation and competitiveness through better interaction among the business and research actors;

b) Entrepreneurial mind sets, skills and attitudes (mainly in the field of food processing, quality and consumer health) strengthened.

## Specific objective(s)

The specific objective of this contract is as follows:

To support the Ministry of Agriculture and Rural Development as the Lead Partner in the development of the Food4Health Technological platform, part of project deliverable 3.3.1 Co-Design & development of the Food4Health technological platform.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Development of Food4health platform created

- Content management of Food4health platform

The electronic platform will become the main tool for sharing information and knowledge and for creating collaboration between young people, businesses, research centers and other key players. The F4H platform will foster interactions and synergies between public authorities, research-business-consumer centers, thus favoring an "open contamination environment".

This platform will be used to provide services ranging from traceability to food education, from the creation and updating of databases on small owners and start-ups, to online repositories on best practices, common guidelines and publications, FAQs related to the agri-food and fisheries sector.

This Food4Health Platform will represent an important tool for the whole public and private system related to food education and consumption, primarily catering services. It’s a tool accessible to everyone, capable of transferring information and sharing useful knowledge to improve the food/human health relationship.

The F4H platform will foster interactions and synergies between public authorities, research-business-consumer centers, thus favoring an "open contamination environment". Important additional targets that will be involved through the platform are: other organizations/regions/countries outside of the current partnership. For instance, other partners and key actors involved in linked projects of the same programme Interreg IT AL MN (i.e Operational Groups - EIP Agri, etc) as well other CTE programs or Horizon 2020 projects.

The main contents and services sessions envisaged in the food4health technological platform will be populated with data and information. Each partner involved in the activity will identify at least an expert technician in charge of developing and continuous updating in progress data and information compared to the advance of design activities until the end of the project, with special reference to the 5 distinctive sessions of the platform.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Continued Government commitment and support IPA CBC Italy-Albania-Montenegro 2014-2020 in Albania.

- Food4Health funds available

- Project stakeholders are dedicated to participate and cooperate throughout the project

- All project partners will be dedicated to communicate and report adequately

- Set up collaborative approach with local stakeholders, sectoral (agri-food and fishery) associations, regional institutes and scientific actors

## Risks

- Lack of willingness of the stakeholders to participate

- Inputs provided by stakeholders are not sufficient in quantitative or qualitative manner

- Delay in implementation of activities and deliverables by respective partners

- Poor communication with and between partners;

- No funds available

# SCOPE OF THE WORK

## General

### Description of the assignment

This assignment is related to work package WPT3 in the frame of the activity about the the creation of the “Food4Health technological platform” with advanced tools and services to promote quality food and consumer health. The implementation and continuous populating of the food4health web platform represent a major tool for the whole program area in order to transfer and share knowledge and services targeted to develop entrepreneurship and competitiveness of enterprises. For this reason, a participatory methodological approach will be used for the content management and population with data of the platform in order to listen to the needs of stakeholders and the main users of the tool and capacity building of Albanian stakeholders to use the platform. This platform will be open source thus ensuring access to all stakeholders, so they can after change and update their data that will be prepared and uploaded in the platform during this phase of the project.

### Geographical area to be covered

Albania

### Target groups

Target groups of such task will be:

- Public authorities (at local, regional and national level) involved in the best practices (B.C) exchange in food quality and consumer health.

- Businesses, economic operators and MSMEs involved as potential beneficiaries of the project to learn about the promoted B.C and will participate in the co-design of the food schemes (procurements) with a participatory approach improving the concrete impact of the results.

- Institutional stakeholders, research centres, as well as MSMEs to represent, as key actors, the common model “Food4Health”.

- Project Partners

- General public

## Specific work

The activity of content management of the platform is related to project deliverable 3.3.1 Co-Design & development of the Food4Health technological platform.

The assignment includes targeted meetings with the enterprises and public bodies (research bodies, municipalities, authorities responsible for human health and education, doctors, etc.) and private entities (ex. catering services), who are direct beneficiaries and stakeholders of the Food4Health project to identify and develop content about their services that support the process to improve quality and safety of food products and the quality of life and human wellbeing.

During this assignment the experts will help these target groups to create content and upload their data in the platform. Part of the assignment is the organization of capacity building meetings with Albanian stakeholders to help them to use the platform.

The major though not exhaustive themes of the contents and services of users / target groups that will be uploaded in the platform are:

1) traceability of products origin,

2) food education,

3) innovation demand and supply,

4) animation of virtual community of practices,

5) database start-up and innovative SMEs

The expert will work with the Albanian target groups to create content and written materials or other tools to be uploaded in the platform.

This cross-border food4health technological platform (Output: F4H platform) and the content that will be uploaded with the help of this contract will deliver information about Albanian local stakeholder and their services about how to improve food products quality and safety as well as about the importance of food for nutrition and quality of life - including the possible role of public and private institutions involved in health management - will be implemented.

The expert will organize three capacity building meetings with Albanian stakeholders, in Tirana, Vlora and Korca to encourage the use of advanced ITC (F4H platform) and to connect with similar companies in Italy and Montenegro, users of the platform. At least 15 stakeholders should take part in each meeting. These meeting will encourage the use of advanced ITC (Food4Health platform, open databases and ITC tools) by Albanian stakeholders and fostering, throughout the project, interactions and synergies between public authorities-enterprises-consumers and favoring an “open contamination environment”.

The information that will be uploaded in the platform by the expert will be English and Albanian.

## Project management

### Responsible body

The Directorate for Implementation of Priorities and Statistics in the Ministry of Agriculture and Rural Development in Albania will be responsible for managing this contract. The contractor will report to the MARD Project Coordinator of Food4Health Project.

### Management structure

The Contractor will be responsible for implementation of the contract under the overall direction of the Project Working Group appointed by MARD.

In every case the Contractor shall obtain approval by the MARD Project Coordinator before exercising any authority for which he is required to obtain prior authorization. Furthermore, he will not be entitled to make decisions on time extension without prior approval under this contract.

### Facilities to be provided by the contracting authority and/or other parties

The Contractor shall ensure the facilities for the conduction assignment and space is provided.

# LOGISTICS AND TIMING

## Location

Albania

## Start date & period of implementation of tasks

The intended start date is September 2022 and the period of implementation of the contract will be 5 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

### Other experts, support staff & backstopping

Key experts are defined and they must submit CVs and signed statements of exclusivity and availability.

1 (one) Key expert is intended to be recruited under this assignment with the following qualifications:

Key expert

Qualifications and skills

- Master degree, or equivalent, in Information Technology, Agriculture, Public Policy and Administration, Economics, Development Studies or a directly related discipline or equivalent;

- Excellent command of English language;

General professional experience

- Preferably 10 (ten) years but not less than 7 (seven) years of professional experience.

General professional experience

- At least 5 years’ experience of implementing projects with public sector/national authorities

- Experience in working with EU-funded projects

- Professional experience in Albania

Specific professional experience

- Preferably 5 (five) years but not less than 3 (three) years of professional experience in related fields;

- Specific trainings in the areas of IT content management, preferably in agriculture development, and/or the economics of rural development, development studies with a focus on agriculture;

- Proven practical experience on developments of platforms and content management.

## Office accommodation

Office accommodation is to be provided by the Contractor

## Facilities to be provided by the contractor

Not applicable

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English language in 2 (two) original copies and 1 (one copy) for archiving purposes:

- Inception report - Maximum of maximum 10 pages to be produced after one week, from the start of implementation. In the report the Contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The Contractor should precede with his/her work unless the Contracting Authority sends comments on the inception report.

- Draft final report of maximum 20 pages. This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final Report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 30 days after receipt of comments on the draft final report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final reports must be provided along with 2 copies of all deliverables and the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

The reports must be written in English, complying with the programme templates.

The MARD Project Coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

- Reports timely submitted and approved

- Timely submission of the deliverables of the project in compliance with ToRs

- Work completed and handed over in time

## Special requirements

Not applicable

* * *