REQUEST FOR EXPRESSIONS OF INTEREST (RfEoI)

(CONSULTING SERVICES)

Firms Selection

Climate Resilience and Agriculture Development Project in Albania

Project ID Number: No.: P178715

IBRD Loan Number: 94890

Assignment Title: “Project monitoring and evaluation (baseline, midterm and final”

Refertence: AL-MARD-493935-CS-CQS

- The World Bank is assisting the Government of Albania (GoA) with the financing of the Climate Resilience and Agriculture Development project (CRAD). This project aims to increase competitiveness and climate resilience of priority agri-food value chains focusing on (i) promoting climate smart and resilient value chains,  (ii) promoting typical products and value addition (iii) developing Climate Smart Agriculture (CSA) IT Platform (iv) modernizing selected irrigation and drainage schemes for high-value agricultural production (v) enhancing compliance with food safety and quality standards and (vi) strengthening evidence-based decision making for resilience and sustainable agri-food systems.

The services required to be contracted aim to support the Ministry of Agriculture and Rural Development (MARD) in ensuring successful implementation of the contract reference “AL-MARD-493935-CS-CQS”.

The objective of the assignment is to achieve the Project Development Objective (PDO) and intermediate indicators. The Project evaluation and Beneficiaries Survey is an essential requirement.

It is important to very clearly describe that there are two complementary activities:

- Outcome evaluation (Quantitative Analysis)

- Process Evaluation (Qualitative Analysis)

And that the methodologies for both are supporting each other and need beneficiary survey (for quantitative data) and focus group discussion with beneficiaries and implementers (for qualitative analysis).

The monitoring and evaluation system of the project will support continuous data collection within the Result Framework for all project components to ensure:

- a baseline assessment of project monitoring indicators,

- a mid-term monitoring survey to support a project review based on regular monitoring and evaluation of results and

- an end-of-project survey to support project impact assessment.

The assessment of the project monitoring indicators will be designed to reflect the project programmatic structure, institutions involved, and geographic distribution of the beneficiaries.

To achieve the objectives of this assignment, the Consulting Company responsible for Project monitoring and evaluation (baseline, midterm and final will carry out the following tasks/ activities to satisfy the client and standard practices, as described below.  The Consultant will provide full services during the contract performance.

# Scope of Work

The scope of work will include::

To effectively achieve the objectives of the Consultancy Services the Consultant will be responsible for providing all required services and mobilizing a collaborative team of qualified professional staff during the execution of the Consultancy Services.

The Scope of Work of the Consultancy Services shall comprise, but not necessarily be limited to the following tasks:

- Situation analysis and methodological approach

- Design and carry out of a Beneficiary Survey

- Assessment of the impact of the Project results

The Ministry of Agriculture and Rural Development now invites eligible consulting firms (“Consultants”) to indicate their interest in providing the Services.  Interested Consultants should provide information demonstrating that they have the required qualifications and relevant experience to perform the Services.

The Consultants may collaborate with each other in the form of a joint venture or a sub-consultancy agreement to complement their respective areas of expertise, strengthen their technical accountability towards their proposals, provide a larger group of experts, and offer better approaches and methodologies.

The Consultant shall be a firm or a group of firms/consultants with the following minimum qualifications:

- The Consultant must be a reputable consulting firm/group of consultants with demonstrable knowledge and at least 10 years of experience in Monitoring & Evaluation Consultancy, Survey assignment, etc.

- Similar contracts completed within the last 5 (five) years (must have completed at least 2 similar contracts in the last 5 years in Monitoring & Evaluation Consultancy, Survey assignment, etc.)

- Previous experience with World Bank projects will be an advantage.

Applicants will be evaluated to determine a shortlist of the most qualified firms. The criteria to be used for the selection of the shortlist will be as follows:

- Core business and years in business – 30 points

- Previous experience in similar tasks – 60 points

- Availability of qualified staff within the firm to carry out the task – 10 points

The CVs of key experts will not be evaluated during the shortlist process.

The CVs of key experts will be evaluated after the issuance of the Request for Technical and Financial Proposals for the consultant selected at the top of the shortlist.  The evaluation will be conducted in accordance with the evaluation criteria specified and detailed in the Request for Proposal.

The Consultant will provide approximately 64.50 person-months of key staff.  This assignment will be undertaken by a Consultant Company, qualified and experienced in the Evaluation of Project outcomes and Beneficiaries Survey, with proven good records of accomplishment. High degree of flexibility and ability to meet strict deadlines will be required.

The attention of interested Consultants is drawn to Section III, paragraphs, 3.14, 3.16, and 3.17 of the World Bank’s “Procurement Regulations for IPF Borrowers” July 2016 revised November 2020 (“Procurement Regulations”), setting forth the World Bank’s policy on conflict of interest.

Consultants may associate with other firms to enhance their qualifications but should indicate clearly whether the association is in the form of a joint venture and/or a sub-consultancy. In the case of a joint venture, all the partners in the joint venture shall be jointly and severally liable for the entire contract, if selected.

The consultant will be selected based on quality-based selection (CQS) method in accordance with the procedures set out in the World Bank’s Procurement Regulations for IPF Borrowers, Procurement in Investment Project Financing Goods, Works, Non-Consulting and Consulting Services July 2016 (revised November 2020).

Interested Consultants may obtain further information concerning the Terms of Reference at the official website of MARD: https://bujqesia.gov.al/projekti-qendrueshmeria-ndaj-klimes-dhe-zhvillimit-ne-bujqesi/, or at the address below, during office hours 09:00 to 16:00 (Monday to Thursday) and 09:00 to 13:00 on Friday.

Expressions of Interest (EoI) in English language must be delivered no later than June 26, 2025 hardcopy (in person or by mail) to the address below, within office hours, and/or electronically at the below e-mail address.

Ministry of Agriculture and Rural Development

Adr: Blv. "Dëshmorët e Kombit", Nr. 2, 1001, Tirana, Albania

E-mail: arben.molla@bujqesia.gov.al

Attn:	Mr. Arben Molla

Project Manager